## Timeline
2023 ON TOUR EVENT 12-WEEK PLANNING TIMELINE
| STARTING OFF | 12 WEEKS | 11 WEEKS | 10 WEEKS | 9 WEEKS | 8 WEEKS | 7 WEEKS | 6 WEEKS
| Review Welcome Aboard email | Send shipping address to WSFF | Post event on community calendars | Begin building your film program | Review graphics and media guidelines | Finalize your ticketing plan with WSFF | Evaluate membership strategy | Submit a draft of your film program and run of show to WSFF for approval
| Schedule a kickoff call / update call | Start (or continue) with sponsorship solicitations | View full-length films (links in Resources) | Customize your press release | Start promotions across social media | Evaluate media and outreach efforts | Establish a membership incentive (if applicable) | Solicit in-kind advertisements with local papers or stations
| Book event venue and discuss safety protocols | Build out your marketing and outreach strategy | Establish your membership strategy | Consider a direct mailer Save the Date | Build a Facebook event page & link WSFF | Target 5+ community groups to invite | Solicit in-kind donations for raffle items or door prizes | Start selling tickets
| Assemble your event committee and hold your first meeting | Review film synopses and categories | Begin to develop your ticketing tiers | Schedule email/newsletter outreach | Obtain hi-resolution logos from sponsors | Email your database - 2 months out! | Invite people outside of your circle to the event | Work on your program and other needed graphics
| Review marketing and outreach guidelines in Resources | Contact filmmakers or local speakers to get involved in your event | Place order for Klean Kanteen cups (optional) | Determine needed volunteer positions (pre-event and day of) | Create or request your poster | Schedule ads and interviews | Work on your emcee scripts | Consider adding musical performances or an art show to your in-person event
| Confirm your event date with WSFF | Send shipping address to WSFF | Request SNBC in-kind donations (optional) | Invite local non-profits and community groups to get involved | Start working on first draft of your film program | Finalize your emcee and speakers list | Prepare your film draft film program
| Set messaging, attendance, membership, a monetary goals |  |  | Initiate converstaion with restaurant partners (optional) |  | Recruit volunteers | Finalize your poster and start printing
| Build a local sponsorship list and create a sponsorship plan |  |  |  |  | Secure technical equipment needs and permits (as applicable)
Watch for delivery of your National Partner Kit
Excel Sheet Printing Instructions:
Print Active Sheets
Landscape Orientation
Ledger 11 x 17
Narrow Margins
Fit Sheet To One Page
| 5 WEEKS | 4 WEEKS | 3 WEEKS | 2 WEEKS | 1 WEEK | WEEK OF | DAY OF | AFTERWARDS
| Finalize any ingestion films | Finalize your job ticket for production with WSFF | Follow up with local media outlets, newspapers, and radio/TV stations | Download your MP4 file program and test with your venue | Check in with your sponsors and other invited guests | Final push for attendance | Send reminder email to attendees with instructions | Complete debrief call with WSFF
| Create your custom host/sponsor slides and upload to Dropbox | Assess outreach effectiveness and membership incentives | Repost all social media blasts | Pay your balance to WSFF | Confirm with your volunteers | Hold radio interviews | Arrange space at venue for sponsors, concessions, etc. | Return banners to WSFF with prepaid mailer and delete your MP4 program
| Upload your logo to Dropbox | Continue to distribute posters | Promote your films, your speakers, and share what makes your event great! | Keep promoting on social media, invite your friends and connections | Confirm with all vendors and partners | Run through script with your emcee | Bring supplies to venue and pick up rentals as needed | Inventory supplies
| Print and distribute posters and postcards locally | Re-post on social media and share film stills | Finalize and print your paper program | Finalize your staff and volunteer plans | Finalize your in-person emcee script and run of show (if applicable) | Review run of show with your venue | Setup supplies, tables, and greening stations | Debrief with your committee and key volunteers
| Confirm raffle and/or auction items | Confirm all logistics with your venue | Collect raffle and/or auction items | Plan for a final e-blast and event reminder | Finalize your food & beverage plan | Prep all supplies, print lists, and make any last minute purchases | Meet with emcee, stage manager, and AV tech to test equipment | Send pictures to WSFF (if applicable)
| Attend community events and share yours | Continue volunteer recruitment | Finalize your day of plan - attendee flow, branding and dressing, greening, etc. | Your biggest outreach push yet to sell those tickets! | Seek out opporutnities for last minute promotions | Collect all raffle and/or silent auction items | Review protocol with staff & volunteers | Pull attendance reports
|  | Email your database - 1 month to go! | Draft your in-person run of show |  | Re-poster as necessary |  | Take pictures! | Reconcile memberships, raffle ticket purchases, donations, etc.
[5 empty] | Build your venue supply list and prep signs, decorations, etc. |  |  | Send thank yous to attendees, new members, and volunteers
[5 empty] | Keep selling those tickets!! |  |  | Schedule follow-up membership letter
Get ready for next year!